## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-01 | Create GitHub Repository and Branch Structure | MUST HAVE | None | Vyshnavi | 3- Completed
1 | 1 | US-02 | Install Java JDK (17+) and Configure Development Environment | MUST HAVE | None | Entire team | 3- Completed
1 | 1 | US-03 | Install IntelliJ IDEA and Configure Spring Boot Project | MUST HAVE | US-02 | Entire team | 3- Completed
1 | 1 | US-04 | Configure MySQL and Establish Database Connectivity | MUST HAVE | US-03 | Entire team | 3- Completed
1 | 1 | US-05 | Create React + Vite Frontend Project Structure | MUST HAVE | US-01 | Frontend Team | 3- Completed
1 | 1 | US-06 | Configure React Router, Bootstrap and Project Folder Structure | MUST HAVE | US-05 | Frontend Team | 3- Completed
1 | 1 | US-07 | Prepare Business Requirement (R&D) Document | MUST HAVE | None | Krina | 3- Completed
1 | 1 | US-08 | Design Business Workflow | MUST HAVE | US-07 | Krina | 3- Completed
1 | 1 | US-09 | Design Eligibility logic workflow | MUST HAVE | US-08 | Vyshnavi | 3- Completed
1 | 1 | US-10 | Design Entity Relationship(ER) Diagram | MUST HAVE | US-07 | Krina | 3- Completed
1 | 1 | US-11 | Design Database Tables | MUST HAVE | US-10 | Krina | 3- Completed
1 | 1 | US-12 | Prepare REST API Design Document | MUST HAVE | US-10 | Backend Team | 3- Completed
1 | 1 | US-13 | Created Home Page UI | MUST HAVE | US-06 | Vyshnavi | 3- Completed
1 | 1 | US-14 | Develop User Login Page | MUST HAVE | US-13 | Vyshnavi | 3- Completed
1 | 1 | US-15 | Develop User Registration Page | MUST HAVE | US-13 | Vyshnavi | 3- Completed
1 | 1 | US-16 | Develop Forgot Password Page | SHOULD HAVE | US-14 | Vyshnavi | 3- Completed
1 | 1 | US-17 | Design Beneficiary Dashboard UI | SHOULD HAVE | US-14 | Vyshnavi | 3- Completed
1 | 1 | US-18 | Develop Government Schemes Listing Page | SHOULD HAVE | US-17 | Deepak Priyan | 3- Completed
1 | 1 | US-19 | Develop Scheme Details Page | MUST HAVE | US-18 | Deepak Priyan | 3- Completed
1 | 1 | US-20 | Develop Common Application Form | MUST HAVE | US-19 | Deepak Priyan | 3- Completed
1 | 1 | US-21 | Develop My Applications page | MUST HAVE | US-17 | Deepak Priyan | 3- Completed
1 | 1 | US-22 | Develop Track Application Page | SHOULD HAVE | US-21 | Deepak Priyan | 3- Completed
1 | 1 | US-23 | Develop Beneficiary Profile Page | MUST HAVE | US-17 | Deepak Priyan | 3- Completed
1 | 1 | US-24 | Design Front Desk Officer Dashboard UI | MUST HAVE | US-17 | Hasini | 3- Completed
1 | 1 | US-25 | Develop Application Management Features (Search, Filter, Forward, Reject) | MUST HAVE | US-24 | Hasini | 3- Completed
1 | 1 | US-26 | Implement Sidebar and Top Navigation for Front Desk Dashboard | SHOULD HAVE | US-24 | Hasini | 3- Completed
1 | 1 | US-27 | Implement View Application Details Modal | SHOULD HAVE | US-25 | Hasini | 3- Completed
2 | 2 | US-28 | Develop Beneficiary & Scheme Management APIs | SHOULD HAVE | US-10 | Chaitanya | 3- Completed
2 | 2 | US-29 | API Testing for Beneficiary & Scheme Modules | SHOULD HAVE | US-28 | Krina | 3- Completed
2 | 2 | US-30 | Develop Application Submission Module | MUST HAVE | US-07 | Nagulla | 3- Completed
2 | 2 | US-31 | Configure React Router Navigation and Application Routing | MUST HAVE | US-06 | Vyshnavi | 3- Completed
2 | 2 | US-32 | Implement Public Navigation Flow (Home, Login, Register, Browse Schemes, Dashboard | MUST HAVE | US-13 | Vyshnavi | 3- Completed
2 | 2 | US-33 | Integrate Beneficiary Navigation Flow for Scheme Application | MUST HAVE | US-17 | Vyshnavi | 3- Completed
2 | 2 | US-34 | Implement Role Selection Module and User Navigation | SHOULD HAVE | US-14 | Vyshnavi | 3- Completed
2 | 2 | US-35 | Implement the Verification workflow | MUST HAVE | US-07 | Nagulla | 3- Completed
2 | 2 | US-36 | Implement the eligibility scoring logic | MUST HAVE | US-08 | Chaitanya | 3- Completed
2 | 2 | US-37 | API Testing for Application Module | SHOULD HAVE | US-30 | Krina | 3- Completed
2 | 2 | US-38 | Impletment OTP for forgot password | COULD HAVE | US-06 | Chaitanya | 3- Completed
2 | 2 | US-39 | API Testing for OTP | SHOULD HAVE | US-38 | Krina | 3- Completed
2 | 2 | US-40 | API Testing for eligibility scoring logic | SHOULD HAVE | US-36 | Krina | 3- Completed
2 | 2 | US-41 | API Testing for Verification workflow | SHOULD HAVE | US-35 | Krina | 3- Completed
3 | 3 | US-42 | Implement Anlytics Dashboard module | MUST HAVE | US-07 | Krina | 3- Completed
3 | 3 | US-43 | Implement Notification module | MUST HAVE | US-07 | Chaitanya | 3- Completed
3 | 3 | US-44 | Implement audit log module | MUST HAVE | US-07 | Chaitanya | 3- Completed
3 | 3 | US-45 | Implement finance approver module | MUST HAVE | US-07 | Nagulla | 3- Completed
3 | 3 | US-46 | Implement disbursement plan module | MUST HAVE | US-07 | Nagulla | 3- Completed
3 | 3 | US-47 | Implement Disbursement Stage Configuration & Amount Validation | MUST HAVE | US-46 | Krina | 3- Completed
3 | 3 | US-48 | Implement Sequential Staged Release with Transactional Audit & Budget Update | MUST HAVE | US-47 | Krina | 3- Completed
3 | 3 | US-49 | Implement Daily Reminder & Overdue Flagging Schedulers | MUST HAVE | US-43 | Krina | 3- Completed
3 | 3 | US-50 | Implement Admin Override for Overdue Milestone Resolution | MUST HAVE | US-49 | Krina | 3- Completed
3 | 3 | US-51 | Enhance Analytics Dashboard with Compliance Rate & Regional Disbursement Totals | MUST HAVE | US-42 | Krina | 3- Completed
3 | 3 | US-52 | Integrate Beneficiary Dashboard APIs | MUST HAVE | US-17 | Deepak Priyan | 3- Completed
3 | 3 | US-53 | Integrate Beneficiary Profile APIs | MUST HAVE | US-23 | Deepak Priyan | 3- Completed
3 | 3 | US-54 | Integrate Application Form APIs | MUST HAVE | US-20 | Deepak Priyan | 3- Completed
3 | 3 | US-55 | Integrate Application Timeline APIs | SHOULD HAVE | US-22 | Deepak Priyan | 3- Completed
3 | 3 | US-56 | Create Beneficiary API Service Layer | MUST HAVE | US-31 | Deepak Priyan | 3- Completed
3 | 3 | US-57 | Configure Beneficiary API Routing | MUST HAVE | US-56 | Deepak Priyan | 3- Completed
3 | 3 | US-58 | Develop Disbursement / Milestone Tracker UI | MUST HAVE | US-55 | Deepak Priyan | 3- Completed
3 | 3 | US-59 | Develop Notifications Panel UI | SHOULD HAVE | US-58 | Deepak Priyan | 3- Completed
3 | 3 | US-60 | Develop Verification Dashboard UI | MUST HAVE | US-35 | Hasini | 3- Completed
3 | 3 | US-61 | Develop Finance Dashboard UI | MUST HAVE | US-35 | Hasini | 3- Completed
3 | 3 | US-62 | Develop Department Admin Dashboard UI | MUST HAVE | US-35 | Hasini | 3- Completed
3 | 3 | US-63 | Develop Super Admin Dashboard UI | SHOULD HAVE | US-62 | Hasini | 3- Completed
3 | 3 | US-64 | Develop Reports Dashboard UI | SHOULD HAVE | US-62 | Hasini | 3- Completed
3 | 3 | US_65 | Integrate Login API with Backend | MUST HAVE | US-37 | Vyshnavi | 3- Completed
3 | 3 | US-66 | Integrate Registration API with Backend | MUST HAVE | US-37 | Vyshnavi | 3- Completed
3 | 3 | US-67 | Implement Role-Based Authentication & Navigation | MUST HAVE | US-65,US-66 | Vyshnavi | 3- Completed
3 | 3 | US-69 | Develop Audit Log Viewer (Super Admin) UI | MUST HAVE | US-63 | Vyshnavi | 3- Completed
3 | 3 | US-70 | Develop Fund Utilization / Regional Analytics Dashboard UI | SHOULD HAVE | US-42 | Vyshnavi | 3- Completed
3 | 3 | US-71 | Implement PDF & Excel Scheme-Summary Report Export | MUST HAVE | US-51 | Krina | 3- Completed
3 | 3 | US-72 | Fix Role-Based Access Control Enforcement (Method Security) | MUST HAVE | US-71 | Krina | 3- Completed
4 | 4 | US-73 | Benificiary Dashboard Enhancements added status tracker for application | MUST HAVE | US-23 | Krina | 3- Completed
4 | 4 | US-74 | Benificiary Dashboard Integrated with Backend | MUST HAVE | US-74, US-23 | Krina | 3- Completed
4 | 4 | US-75 | Front Desk Officer Dasboard Integrated with Backend | MUST HAVE | US-24 | Hasini | 3- Completed
4 | 4 | US-76 | Verification Officer Dashboard Integrated with Backend | MUST HAVE | US-60 | Hasini | 3- Completed
4 | 4 | US-77 | Super Admin Dashboard Integrated with Backend | MUST HAVE | US-63 | Vyshnavi | 3- Completed
4 | 4 | US-78 | Finance Officer Dashboard Integrated with Backend | MUST HAVE | US-61 | Nagulla | 3- Completed
4 | 4 | US-79 | Disbursement Officer Dashboard Integrated with Backend | MUST HAVE | US-61 | Deepak | 3- Completed
4 | 4 | US-80 | Testing the Application workflow | MUST HAVE | - | Chaitanya | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 577 | 332 | 127 | 43 | 28 | 9 | 13 | 16 | 6 | 1 | 2 | 4 | 2 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T1 | Create GitHub Repository and Branch Structure | 2026-06-29 | 2026-06-29 | Vyshnavi | Setup | 3- Completed | 3 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T1 | Install Java JDK (17+) and Configure Development Environment | 2026-06-29 | 2026-06-29 | Entire Team | Setup | 3- Completed | 3.5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T1 | Install IntelliJ IDEA and Configure Spring Boot Project | 2026-06-30 | 2026-06-30 | Entire Team | Setup | 3- Completed | 3.5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T1 | Configure MySQL and Establish Database Connectivity | 2026-07-01 | 2026-07-01 | Entire Team | Setup | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T1 | Create React + Vite Frontend Project Structure | 2026-06-29 | 2026-06-29 | Frontend Team | Setup | 3- Completed | 5 | 2 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T1 | Configure React Router, Bootstrap and Project Folder Structure | 2026-06-30 | 2026-06-30 | Frontend Team | Setup | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T1 | Prepare Business Requirement (R&D) Document | 2026-06-29 | 2026-06-29 | Krina | Design | 3- Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T1 | Design Business Workflow | 2026-06-30 | 2026-06-30 | Krina | Design | 3- Completed | 5 | 2 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T1 | Design Eligibility Logic Workflow | 2026-06-30 | 2026-06-30 | Vyshnavi | Design | 3- Completed | 5 | 5 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T1 | Design Entity Relationship (ER) Diagram | 2026-07-01 | 2026-07-01 | Krina | Design | 3- Completed | 5 | 5 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T1 | Design Database Tables | 2026-07-02 | 2026-07-03 | Krina | Build | 3- Completed | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T1 | Prepare REST API Design Document | 2026-06-29 | 2026-06-29 | Backend Team | Design | 3- Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T1 | Create Home Page UI | 2026-07-01 | 2026-07-02 | Vyshnavi | Build | 3- Completed | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | T1 | Develop User Login Page | 2026-07-03 | 2026-07-06 | Vyshnavi | Build | 3- Completed | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T1 | Develop User Registration Page | 2026-07-07 | 2026-07-08 | Vyshnavi | Build | 3- Completed | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | T1 | Develop Forgot Password Page | 2026-07-09 | 2026-07-10 | Vyshnavi | Build | 3- Completed | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T1 | Design Beneficiary Dashboard UI | 2026-07-13 | 2026-07-13 | Vyshnavi | Design | 3- Completed | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | T1 | Develop Government Schemes Listing Page | 2026-06-29 | 2026-06-30 | Deepak Priyan | Build | 3- Completed | 6 | 3 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-19 | T1 | Develop Scheme Details Page | 2026-07-01 | 2026-07-02 | Deepak Priyan | Build | 3- Completed | 7 | 3 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-20 | T1 | Develop Common Application Form | 2026-07-03 | 2026-07-06 | Deepak Priyan | Build | 3- Completed | 7 | 1 | 1 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-21 | T1 | Develop My Applications Page | 2026-07-07 | 2026-07-08 | Deepak Priyan | Build | 3- Completed | 6 | 2 | 1 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-22 | T1 | Develop Track Application Page | 2026-07-09 | 2026-07-10 | Deepak Priyan | Build | 3- Completed | 7 | 2 | 1 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-23 | T1 | Develop Beneficiary Profile Page | 2026-07-13 | 2026-07-14 | Deepak Priyan | Build | 3- Completed | 7 | 3 | 1 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-24 | T1 | Design Front Desk Officer Dashboard UI | 2026-06-29 | 2026-06-29 | Hasini | Design | 3- Completed | 6 | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-25 | T1 | Develop Application Management Features (Search, Filter, Forward, Reject) | 2026-06-30 | 2026-07-01 | Hasini | Build | 3- Completed | 8 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-26 | T1 | Implement Sidebar and Top Navigation for Front Desk Dashboard | 2026-07-02 | 2026-07-03 | Hasini | Build | 3- Completed | 11 | 2 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-27 | T1 | Implement View Application Details Modal | 2026-07-06 | 2026-07-07 | Hasini | Build | 3- Completed | 11 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-28 | T1 | Develop Beneficiary & Scheme Management APIs | 2026-07-13 | 2026-07-13 | Chaitanya | Build | 3- Completed | 6 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-29 | T1 | API Testing for Beneficiary & Scheme Modules | 2026-07-13 | 2026-07-13 | Krina | Testing | 3- Completed | 3.5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-30 | T1 | Develop Application Submission Module | 2026-07-13 | 2026-07-14 | Nagulla | Build | 3- Completed | 8 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-31 | T1 | Configure React Router Navigation and Application Routing | 2026-07-14 | 2026-07-15 | Vyshnavi | Build | 3- Completed | 8 | 3 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-32 | T1 | Implement Public Navigation Flow (Home, Login, Register, Browse Schemes, Dashboard) | 2026-07-16 | 2026-07-17 | Vyshnavi | Build | 3- Completed | 11 | 3 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-33 | T1 | Integrate Beneficiary Navigation Flow for Scheme Application | 2026-07-20 | 2026-07-21 | Vyshnavi | Integration | 3- Completed | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-34 | T1 | Implement Role Selection Module and User Navigation | 2026-07-22 | 2026-07-23 | Vyshnavi | Build | 3- Completed | 11 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-35 | T1 | Implement the Verification Workflow | 2026-07-15 | 2026-07-16 | Nagulla | Build | 3- Completed | 11 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-36 | T1 | Implement the Eligibility Scoring Logic | 2026-07-14 | 2026-07-15 | Chaitanya | Build | 3- Completed | 11 | 6 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
US-37 | T1 | API Testing for Application Module | 2026-07-14 | 2026-07-14 | Krina | Testing | 3- Completed | 3.5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-38 | T1 | Implement OTP for Forgot Password | 2026-07-16 | 2026-07-17 | Chaitanya | Build | 3- Completed | 11 | 6 | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-39 | T1 | API Testing for OTP | 2026-07-15 | 2026-07-15 | Krina | Testing | 3- Completed | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-40 | T1 | API Testing for Eligibility Scoring Logic | 2026-07-16 | 2026-07-16 | Krina | Testing | 3- Completed | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-41 | T1 | API Testing for Verification Workflow | 2026-07-17 | 2026-07-17 | Krina | Testing | 3- Completed | 3.5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-42 | T1 | Implement Analytics Dashboard Module | 2026-07-27 | 2026-07-28 | Krina | Build | 3- Completed | 11 | 3 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-43 | T1 | Implement Notification Module | 2026-07-27 | 2026-07-28 | Chaitanya | Build | 3- Completed | 11 | 4 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-44 | T1 | Implement Audit Log Module | 2026-07-29 | 2026-07-30 | Chaitanya | Build | 3- Completed | 11 | 3 | 5 |  | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-45 | T1 | Implement Finance Approver Module | 2026-07-27 | 2026-07-28 | Nagulla | Build | 3- Completed | 11 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-46 | T1 | Implement Disbursement Plan Module | 2026-07-29 | 2026-07-30 | Nagulla | Build | 3- Completed | 11 | 3 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-47 | T1 | Implement Disbursement Stage Configuration & Amount Validation | 2026-07-29 | 2026-07-30 | Krina | Build | 3- Completed | 8 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
US-48 | T1 | Implement Sequential Staged Release with Transactional Audit & Budget Update | 2026-07-31 | 2026-08-03 | Krina | Build | 3- Completed | 11 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-49 | T1 | Implement Daily Reminder & Overdue Flagging Schedulers | 2026-08-04 | 2026-08-05 | Krina | Build | 3- Completed | 11 | 6 | 3 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-50 | T1 | Implement Admin Override for Overdue Milestone Resolution | 2026-08-06 | 2026-08-07 | Krina | Build | 3- Completed | 11 | 6 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-51 | T1 | Enhance Analytics Dashboard with Compliance Rate & Regional Disbursement Totals | 2026-08-10 | 2026-08-11 | Krina | Build | 3- Completed | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-52 | T1 | Integrate Beneficiary Dashboard APIs | 2026-07-27 | 2026-07-28 | Deepak Priyan | Integration | 3- Completed | 7 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-53 | T1 | Integrate Beneficiary Profile APIs | 2026-07-29 | 2026-07-30 | Deepak Priyan | Integration | 3- Completed | 7 | 2 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-54 | T1 | Integrate Application Form APIs | 2026-07-31 | 2026-08-03 | Deepak Priyan | Integration | 3- Completed | 7 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-55 | T1 | Integrate Application Timeline APIs | 2026-08-04 | 2026-08-05 | Deepak Priyan | Integration | 3- Completed | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-56 | T1 | Create Beneficiary API Service Layer | 2026-08-06 | 2026-08-06 | Deepak Priyan | Setup | 3- Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-57 | T1 | Configure Beneficiary API Routing | 2026-08-07 | 2026-08-10 | Deepak Priyan | Build | 3- Completed | 8 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-58 | T1 | Develop Disbursement / Milestone Tracker UI | 2026-08-11 | 2026-08-12 | Deepak Priyan | Build | 3- Completed | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-59 | T1 | Develop Notifications Panel UI | 2026-08-13 | 2026-08-14 | Deepak Priyan | Build | 3- Completed | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-60 | T1 | Develop Verification Dashboard UI | 2026-07-27 | 2026-07-28 | Hasini | Build | 3- Completed | 7 | 4 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-61 | T1 | Develop Finance Dashboard UI | 2026-07-29 | 2026-07-30 | Hasini | Build | 3- Completed | 7 | 3 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-62 | T1 | Develop Department Admin Dashboard UI | 2026-07-31 | 2026-08-03 | Hasini | Build | 3- Completed | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-63 | T1 | Develop Super Admin Dashboard UI | 2026-08-04 | 2026-08-05 | Hasini | Build | 3- Completed | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-64 | T1 | Develop Reports Dashboard UI | 2026-08-06 | 2026-08-07 | Hasini | Build | 3- Completed | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-65 | T1 | Integrate Login API with Backend | 2026-07-27 | 2026-07-28 | Vyshnavi | Integration | 3- Completed | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-66 | T1 | Integrate Login API with Backend | 2026-07-29 | 2026-07-30 | Vyshnavi | Integration | 3- Completed | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-67 | T1 | Implement Role-Based Authentication & Navigation | 2026-07-31 | 2026-08-03 | Vyshnavi | Build | 3- Completed | 11 | 5 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-69 | T1 | Develop Audit Log Viewer (Super Admin) UI | 2026-08-04 | 2026-08-05 | Vyshnavi | Build | 3- Completed | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-70 | T1 | Develop Fund Utilization / Regional Analytics Dashboard UI | 2026-08-06 | 2026-08-07 | Vyshnavi | Build | 3- Completed | 7 | 3 | 1 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-71 | T1 | Implement PDF & Excel Scheme-Summary Report Export | 2026-08-12 | 2026-08-13 | Krina | Build | 3- Completed | 11 | 4 | 5 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-72 | T1 | Fix Role-Based Access Control Enforcement (Method Security) | 2026-08-14 | 2026-08-14 | Krina | Bug Fix | 3- Completed | 4.5 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-73 | T1 | Beneficiary Dashboard Enhancements - Added Status Tracker for Application | 2026-08-17 | 2026-08-18 | Krina | Build | 3- Completed | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-74 | T1 | Beneficiary Dashboard Integrated with Backend | 2026-08-19 | 2026-08-20 | Krina | Integration | 3- Completed | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0
US-75 | T1 | Front Desk Officer Dashboard Integrated with Backend | 2026-08-10 | 2026-08-11 | Hasini | Integration | 3- Completed | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-76 | T1 | Verification Officer Dashboard Integrated with Backend | 2026-08-12 | 2026-08-13 | Hasini | Integration | 3- Completed | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-77 | T1 | Super Admin Dashboard Integrated with Backend | 2026-08-10 | 2026-08-11 | Vyshnavi | Integration | 3- Completed | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-78 | T1 | Finance Officer Dashboard Integrated with Backend | 2026-08-10 | 2026-08-11 | Nagulla | Integration | 3- Completed | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0
US-79 | T1 | Disbursement Officer Dashboard Integrated with Backend | 2026-08-10 | 2026-08-11 | Deepak Priyan | Integration | 3- Completed | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-80 | T1 | Testing the Application Workflow | 2026-08-10 | 2026-08-11 | Chaitanya | System Test | 3- Completed | 10 | 4 | 4 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on eligibility and workflow requirements across different government schemes | Conducted a detailed discussion with mentors and reviewed the R&D document to align on scope
Sprint 1 | Day 4 | Ambiguity in ER diagram design for dynamic eligibility fields and multi-scheme data | Held a team brainstorming session and revised the schema design with mentor input
Sprint 1 | Day 8 | Environment inconsistency while configuring Spring Boot, MySQL and React setup across machines | Paired up team members to standardize local environment setup and documented the steps
Sprint 2 | Day 3 | Difficulty designing eligibility scoring logic to handle multiple, varying scheme criteria | Broke the logic into smaller rule-based scoring modules and validated with sample scheme data
Sprint 2 | Day 5 | OTP delivery failing intermittently during forgot-password testing | Debugged the mail configuration and added retry handling for OTP dispatch
Sprint 2 | Day 9 | Confusion over application submission workflow state transitions between roles | Mapped the workflow states in a diagram and aligned the team before continuing development
Sprint 3 | Day 2 | Sequential staged disbursement release causing transactional/budget inconsistencies | Refactored the release logic using database transactions with rollback handling
Sprint 3 | Day 6 | Delay integrating Beneficiary, Verification and Finance dashboard APIs in parallel | Set up a shared integration checklist and daily sync between frontend and backend team
Sprint 3 | Day 9 | Role-based access control not enforced correctly on some backend endpoints | Reviewed and corrected method-level security annotations across affected APIs
Sprint 4 | Day 3 | Discrepancies found while wiring multiple role-based dashboards to the backend | Conducted a joint debugging session across frontend and backend team members
Sprint 4 | Day 7 | Bugs surfaced during end-to-end application workflow testing before sign-off | Logged all defects, prioritized, and fixed them ahead of the internship demo

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-06-29 | 2026-07-10 | Krina | Documenting workflow and design decisions before implementation | Assuming the database schema was final without a review pass | Collaborating closely with mentors during design reviews | Scheduled structured design-review sessions with the team and mentor to finalize the ER diagram and business workflow.
2 | Sprint 2 | 2026-07-13 | 2026-07-24 | Chaitanya | Writing test cases alongside eligibility-logic development | Delaying API testing until the very end of the sprint | Pairing with Krina for API validation and testing | Front-loaded API testing tasks and closed all eligibility-scoring defects before sprint close.
3 | Sprint 3 | 2026-07-27 | 2026-08-07 | Deepak Priyan | Syncing daily on API contracts before starting integration | Building dashboard integrations in isolation without checking backend readiness | Maintaining a consistent UI/API structure across all dashboards | Set up a shared integration checklist and daily sync with the backend team to avoid rework.
4 | Sprint 4 | 2026-08-10 | 2026-08-21 | Vyshnavi | Running full regression checks after each dashboard integration | Marking features complete before role-based access testing was done | Documenting bugs with clear, reproducible steps | Ran end-to-end workflow testing across all six roles and fixed access-control issues before final sign-off.